## Sheet1
Features | Notes | Category | Priority | Status
An intro cut scene to introduce the game |  | Cutscenes | 0 | Done
Figuring out an ending sequence when you defeat a tassie tiger | Display "Guess you're fitter…I'll see you on the chart then, till then..." | Cutscenes | 0 | Done
Controls for touch screens | Four buttons that imitate the arrow keys for keyboards | Controls | 0 | Done
Healing cooldown in battle | Total steps in the game is 12000 Cool down on every 500 steps Heal about 50% original hp Cannot heal more than original hp, if you do, just cap it | Battle | 1 | Done
Healing cooldown outside of battle | Healing outside of battle Should affect the heaing cooldown in battle | Party | 1
Multiplying attack cooldown | Cool down on 700 steps | Battle | 1 | Done
Speed boost cooldown | Cool down on 300 steps | Battle | 1 | Done
Add in cooldowns to battle | Cooldowns should only be used within battles, except healing |  | 1 | Done
Displaying how many steps to the next battle |  | Steps | 2
Showing the next city after conquering the city | Flashing the next city and displaying the steps needed to reach it | Cutscenes | 2
Saving the data so that you can reload the game | Persistent data Figuring out when to save and load | Data | 2
A way to pick a pet | Sort of tied to the intro screen | Party | 3
Figuring out how to "earn" various animals | Tracking a kill count per animal, when you hit the max hp, you can use them Could by extension, use this as the basis for "unlocking" champion and ultimate mode | Party | 3
Adding the ability to "switch" animals | Either in battle or outside of battle Individual stats need to be tracked | Party | 3
Speed up the framerate for fast attacks and slowing the framerate down for slower attacks - easier blocking | Too complicated | Battle | 4 | N/A